## Task_Table
ID | Active | Name | Duration | Start | Finish | Predecessors | Outline Level
1 | Yes | Simply Voting Website Conversion project | 78.5 days | April 3, 2017 8:00 AM | July 20, 2017 12:00 PM |  | 1
2 | Yes | Project planning phase | 2 days | April 3, 2017 8:00 AM | April 4, 2017 5:00 PM |  | 2
3 | Yes | Develop project plan | 2 days | April 3, 2017 8:00 AM | April 4, 2017 5:00 PM |  | 3
4 | Yes | Project analysis phase | 15 days | April 5, 2017 8:00 AM | April 25, 2017 5:00 PM | 3 | 2
5 | Yes | Conduct analysis of SimplyVoting (our target host) | 1 wk | April 5, 2017 8:00 AM | April 11, 2017 5:00 PM |  | 3
6 | Yes | Model data conversion of new system | 1 wk | April 12, 2017 8:00 AM | April 18, 2017 5:00 PM | 5 | 3
7 | Yes | Determine the feasibility of SimplyVoting | 1 wk | April 19, 2017 8:00 AM | April 25, 2017 5:00 PM | 5,6 | 3
8 | Yes | Systems design phase | 10.5 days | April 26, 2017 8:00 AM | May 10, 2017 12:00 PM | 7 | 2
9 | Yes | Review new system's user interface | 3 days | April 26, 2017 8:00 AM | April 28, 2017 5:00 PM |  | 3
10 | Yes | Design the system architecture for any features not offered by SimplyVoting (if any) | 1.5 wks | May 1, 2017 8:00 AM | May 10, 2017 12:00 PM | 9 | 3
11 | Yes | Implementation phase | 31 days | May 10, 2017 1:00 PM | June 22, 2017 12:00 PM | 8 | 2
12 | Yes | Configure the new system | 2 wks | May 10, 2017 1:00 PM | May 24, 2017 12:00 PM |  | 3
13 | Yes | "Go live": official date of transition from legacy to new system | 1 day | May 24, 2017 1:00 PM | May 25, 2017 12:00 PM | 12 | 3
14 | Yes | Train users with the new system | 1 mon | May 25, 2017 1:00 PM | June 22, 2017 12:00 PM | 13 | 3
15 | Yes | Maintenance and support phase | 20 days | June 22, 2017 1:00 PM | July 20, 2017 12:00 PM | 13,14 | 2
16 | Yes | Review the ongoing support of the new system as it's hosted by SimplyVoting | 1 mon | June 22, 2017 1:00 PM | July 20, 2017 12:00 PM |  | 3